## Slide 1: Beardy’s & Okemasis Cree Nation FWI Project
Presented at niita 2023 symposium
Charles Bighead - Project Manager

## Slide 2: Beardy’s & Okemasis Cree Nation
1700 on-reserve members
370 homes

## Slide 3: FWI Solution
10 GB Fiber Backhaul
Two 50m Towers
20 APs (3.65GHz, 5.0 GHz)
~300 Home Installations
GOAL - Connect every home on BOCN

## Slide 4
NE tower
SW Tower

## Slide 5: HOW
Applied to Universal Broadband Fund (UBF) in January 2021
  Rapid Response Stream
  90% Eligible Costs funded by ISED
  10% Eligible Costs + 100% Non-Eligible Costs funded by BOCN
2.2 Million Total Project Cost
Notes: Innovation, Science & Economic Development

## Slide 6: Technology Medium
Copper
  DSL not an option
  Cannot meet 50/10 requirement
Fiber
  Cost Prohibitive
  Short timeline
Wireless
  Terrestrial FWI solution
  Cost effective
  Terrain flat, Short Aspen Trees (LoS)
  Licensed (3.65) and Unlicensed (5.0)

## Slide 7: Internet Service Provider (ISP)
High Speed Internet Backhaul for FWN
 | ISP 1 | SHAW | ISP 3
Medium | Fiber | Fiber | Wireless
Construction | ? | $396,000 $150,000 | $201,000
Rate | 1 GB $4,800/m | 10 GB $3,750/m | 2 GB $8,667/m

## Slide 8: Wireless Consultants
National RFP
  Axsera.com (Quebec)
FWN Turnkey Solution:
  Design, Planning
  Tower Construction
  Radio APs, Installation
  Supply and stage CPE Equipment
Notes: Battle of Duck Lake monument. Start of the Riel Rebellion

## Slide 9: Network & Customer Support
Indigenize Tech
BOCN member owned company
Hired to manage the FWN, provide a helpline and residential support
Hired local band members
Notes: Attended SIIT IT Support Specialist program
iPerf tools to measure maximum bandwidth and dBi values between the homes and the APs
Spectrum Analysis using the AP
Centralized Network Management System

## Slide 10: Project Timeline
2024
2023
2022
2021
UBF Application
Notified July 30 funding approved
ISED negotiations and CA development
Agreements signed Feb 4, 2022
Construction starts
Build towers & install APs
Begin Fiber Construction
OMNITRAX
Waited for railway crossing permit
“Partial” CPE Installs
FWI Go-live
Stabilize & optimize network
Complete Home installs
Develop Sustainability plan

## Slide 11: Network Coverage & Performance
TOWER | Sector | Download | Upload | Aggregate | DBM
North East | 1 | 96.28 | 31.12 | 127.41 | 40.5
 | 2 | 151.98 | 42.9 | 194.88 | 50.5
 | 3 | 96.35 | 32.1 | 128.45 | 37.2
 | 4 | 135.56 | 40.36 | 175.92 | 38.5
 | 5 | 235.25 | 36.03 | 271.3 | 43.8
 | 6 | 234.11 | 40.94 | 275.06 | 50.9
 | 7 | 196.27 | 40.81 | 237.09 | 58.2
 | 8 | 202.38 | 39.81 | 242.2 | 45.9
 | 9 | 180.44 | 35.73 | 216.18 | 62.5
 | 10 | 90 | 42 | 132 | 45.2
 | 11 | 204.8 | 40.43 | 245.24 | 44
 | 12 | 87.14 | 40.94 | 128.08 | 44.2
South West | 1 | 151.9 | 34.47 | 186.37 | 46.5
 | 2 | 76.2 | 12.38 | 88.58 | 61
 | 3 | 147.08 | 25.25 | 172.33 | 48
 | 4 | 96.28 | 17.94 | 114.23 | 50.5
 | 5 | 229.01 | 40.95 | 269.96 | 50.9
 | 6 | 234.02 | 40.94 | 274.96 | 42.2
 | 7 | 235.72 | 40.94 | 276.67 | 47.5
 | 8 | 230.72 | 40.89 | 271.62 | 40

## Slide 12: Subscribers

## Slide 13: ISP Comparisons
BOCN Owned
ISP | Speed (Mbps) | Latency (MS) | Cost | Reliability
WISP 1 | .25 - 1 |  | $150/m > $60/m | Poor
WISP 2 | .25 – 1.2 |  | $150/m | Poor
Starlink | 35 – 85 | 40 | $150/m | Good
BOCN FWI | 55 - 95 | 11 | Free > $75/m | Better
Notes: No Data Caps

## Slide 14: Sustainability
Rate
Subscribers

## Slide 15: Issues
NE Sector 5 AP stopped functioning
Fiber Delay effected home installations
  Required 2-3 visits instead of 1
User Issues
  Resetting routers
  Lost Wi-Fi passcode
LoS, Plow wind
Interference (5GHz)

## Slide 16: Lessons Learned

## Slide 17
Leadership Support
First Nations ownership
Private Sector Partners
Spectrum, ARIN
Internet illiteracy
Project Management, Mitigate Issues
Local Human Resources
Training and Mentoring
Spare Equipment
Communications

## Slide 18: Next Step
Improve mobile communications (voice, text, data)
Spectrum License Holders

## Slide 19
Thank you